## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-MF-120-ME-DW-0020 |  |  |  |  | Vendor Tr. N0: BK-HD-PEDCO-SVTR-MF-0019 |  |  | Transmital Date: 2025/03/25
Document Title: GENERAL ARRANGEMENT FOR RICH-LEAN GLYCOL H.E. (E-200) |  |  |  |  | Client Tr. No: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-MF-120-ME-DW-0020_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Please find the attached comments. |  | BK-SUR-ENG-MEC-03-09955 | 2025-01-19
2 | کلیه نقطه نظرات بر روی Data Sheet ها میبایست بر روی مدارک اعمال گردد. |  | BK-SUR-ENG-MEC-03-09955 | 2025-01-19 | Confirmed.
3 | در خصوص نقشه ها تایپ و نوع انکر بولت ها و ماتریال آن و ...و همخوانی موارد با پروژه نیازمند کنترل می باشد. |  | BK-SUR-ENG-MEC-03-09955 | 2025-01-19 | Confirmed.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 01/19/2025 |  |  |  |  | Date: