## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-MF-120-QC-PR-0012 |  |  |  |  | Vendor Tr. No.: BK-HD-PEDCO-SVTR-MF-0009 |  |  | Transmital Date:2025/04/06
Document Title: Weld Repair Procedure |  |  |  |  | Client Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-MF-120-QC-PR-0012 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عنوان و شماره مدرک با عنوان و شماره مدرک ارائه شده در VPIS مطابقت ندارد. |  |  | 2024-06-01 | The relevant comments in the text have been duly revised/responded to as appropriate.
2 | در بند 3، استاندارد ASME SEC VIII DIV.1 به عنوان رفرنس اضافه گردد. |  |  | 2024-06-01 | The relevant comments in the text have been duly revised/responded to as appropriate.
3 | الزامات استاندارد ASME SEC VIII DIV.1، بعنوان مثال موارد بند UCS-56 در مدرک آورده شود. |  |  | 2024-06-01 | It has been referenced in the reference list.
4 | اقدامات مورد نیاز به منظور جلوگیری از پیشروی ترک در هنگام تعمیر آن، در مدرک آورده شود. |  |  | 2024-06-01 | The relevant comments in the text have been duly revised/responded to as appropriate.
5 | در Weld Repair Report، کلیه موارد مورد نیاز ار جمله Preheat, PWHT(If required), …. آورده شود. |  |  | 2024-06-01 | The relevant comments in the text have been duly revised/responded to as appropriate.
6 | سایر نقطه نظرات روی مدرک درج گردیده است. |  |  | 2024-06-01 | The relevant comments in the text have been duly revised/responded to as appropriate.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: 01-06-2024 |  |  |  |  | Date: